## Milestones
|  | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08
|  | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
PROJECT MILESTONES
OCM MILESTONES
KEY STAKEHOLDERS | Project Team
| Steering Committee & Key Influencers | [47 empty] | d
| Pilot Members | [47 empty] | d
Wave 1 | Leadership (Managers & Supervisors)
End Users
Partners
Wave 2 | Leadership (Managers & Supervisors)
End Users
Partners
Wave 3 | Leadership (Managers & Supervisors)
End Users
Partners
Solution Validated
Sprint II Hardening
User Acceptance Testing
Begin End User Training
Go Live
UAT Communication
Business UAT Planning
UAT Plan Developed
Training Schedule/Plan Defined
Training Notification Message
Blackout Period Restrictions
Finalize Blackout Period Restrictions
Dual Maintenence for Master Data
Dual Maintenence for Master Data
Contract Readiness?
Dual Maintenence for Master Data
Production Cutover
Business Cutover Activities
Finalize Production Cutover Plan/Schedule
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go Live Announcement
Go Live Announcement
Specific Go-Live Instrutions
Integration Update / Outline of Supporting Resources
UAT Communication
Blackout Period Restrictions
Dual Maintenence for Master Data
Business Cutover Activities
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Communicate Production Cutover Results
Communicate Production Cutover Results (Check with Mike)
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Blackout Period Restrictions
UAT
UAT SFO
Integration Testing
1
5
2
3
4
1
5
2
3
4
Wave 2 Training
W1 Go Live
Post Go Live Support
Blackout Period
Go/No Go Checkpoint Report
1
5
2
3
4
1
5
2
3
4
Develop Training & Quick ReferenceGuides
UAT Plan Developed
Training Schedule/Plan Defined
Training Notification Message
Finalize Blackout Period Restrictions
Dual Maintenence for Master Data
Contract Readiness?
Finalize Production Cutover Plan/Schedule
Communicate Production Cutover Results
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Engage Pilot Users
Facilitator, Q&A?
Update
SteerCo
SteerCo
SteerCo
MS Teams Updates
MS Teams Updates
MS Teams Updates
Go Live Announcement
Specific Go-Live Instrutions
Integration Update / Outline of Supporting Resources
UAT Communication
Blackout Period Restrictions
Dual Maintenence for Master Data
Business Cutover Activities
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Communicate Production Cutover Results (Check with Mike)
Quick Start Guides
Training Invite (via teams)
Trg Reminder
Wave 1 Training
Wave 3 Training
MS Teams Updates
MS Teams Updates
Teams Channel?
Pilot Feedback
Wave1 Trg
EMEA, LatAm, Can
Tip of the week
Tip of the week
Tip of the week
1
5
2
3
4
UAT Communication
Business UAT Planning
Blackout Period Restrictions
Dual Maintenence for Master Data
Business Cutover Activities
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go Live Announcement
Go Live Announcement
Specific Go-Live Instrutions
Integration Update / Outline of Supporting Resources
UAT Communication
Blackout Period Restrictions
Dual Maintenence for Master Data
Business Cutover Activities
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Communicate Production Cutover Results (Check with Mike)
Key Stakeholder & Leader Update
Go Live Announcement
Specific Go-Live Instrutions
Integration Update / Outline of Supporting Resources
UAT Communication
Blackout Period Restrictions
Dual Maintenence for Master Data
Business Cutover Activities
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Communicate Production Cutover Results (Check with Mike)
Quick Start Guides
Trg Reminder
Wave 2 Trg
US, Latam
Tip of the week
Specific Go-Live Instrutions
Blackout Period Restrictions
Business Cutover Activities
Communicate Production Cutover Results (Check with Mike)
UAT Communication
Business UAT Planning
Blackout Period Restrictions
Dual Maintenence for Master Data
Business Cutover Activities
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go Live Announcement
Go Live Announcement
Specific Go-Live Instrutions
Integration Update / Outline of Supporting Resources
UAT Communication
Dual Maintenence for Master Data
Business Cutover Activities
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Communicate Production Cutover Results (Check with Mike)
Update
Key Stakeholder & Leader Update
Go Live Announcement
Specific Go-Live Instrutions
Integration Update / Outline of Supporting Resources
UAT Communication
Blackout Period Restrictions
Dual Maintenence for Master Data
Business Cutover Activities
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Go/No Go Checkpoint Report
Communicate Production Cutover Results (Check with Mike)
Quick Start Guides
Trg Reminder
Wave 3 Trg
USA APAC
Tip of the week
Update
Teams Engagement
W2 Go Live
W1 Go Live
Manager & Supervisor Update
Weekly topic
Weekly topic
Weekly topic
Weekly topic
Weekly topic
W2 Go Live
W3 Go Live
Manager & Supervisor Update
Partner instructions (pdf)
Partner instructions (pdf)
Partner instructions (pdf)
W3 Go Live

## Communication Plan
| ID # | CATEGORY | AUDIENCE | DUE DATE | DAYS LEFT | STATUS | % DONE | COMMUNICATION | OBJECTIVES / KEY MSG | VEHICLE (CHANNEL) | TRANSLATION REQUIRED? | ADKAR | FREQUENCY | DEVELOPER | REVIEWERS | OWNER/ SENDER | PLANNED / AD-HOC | NOTES/FEEDBACK/ISSUES
| 3 | SteerCo | Steering Committee | 2020-10-12 | -581 | COMPLETE | 100% | SteerCo call |  |  |  | Awareness
#REF!
#REF!
| #REF! | Monthly Update | Project Team, Pilot Members | 2021-04-24 | -387 | COMPLETE | 100% | MS Teams Update |  |  |  | Awareness
| #REF! | Monthly Update | Project Team, Pilot Members | 2021-05-24 | -357 | COMPLETE | 100% | MS Teams Update |  |  |  | Awareness
#REF!
#REF!
| #REF! | Teams Site - Pilot Users | Pilot Members | 2020-10-26 | -567 | COMPLETE | 100% | Announce MS Teams space for Pilot Members |  |  |  | Awareness |  |  |  | Teams email
| #REF! | Teams Site - Pilot Users | Pilot Members | 2020-11-02 | -560 | COMPLETE | 100% | Walk through team space with Pilot Members |  |  |  | Awareness |  |  |  | Teams email
| #REF! | Teams Site - Pilot Users | Pilot Members | 2020-11-09 | -553 | COMPLETE | 100% | Use MS Forms to send survey |  |  |  | Awareness |  |  |  | Teams email
x | #REF! | Teams Site - Pilot Users | Pilot Members | 2020-11-16 | -546 | COMPLETE | 100% | Share feedback & action items |  |  |  | Awareness |  |  |  | Teams email
#REF!
| #REF! | Wave 1 | Wave 1 End Users | 2020-10-26 | -567 | COMPLETE | 100% | MS Teams Update - Upcoming Training |  |  |  | Awareness
| #REF! | Wave 1 | Wave 1 End Users | 2020-11-02 | -560 | COMPLETE | 100% | Training Invitation | Teams/Outlook calendar hold |  |  | Awareness
| #REF! | Wave 1 | Wave 1 End Users | 2020-11-16 | -546 | COMPLETE | 100% | Training Reminder |  |  |  | Awareness
#REF!
#REF!
| #REF! | Wave 2 | Wave 1 End Users | 2020-10-26 | -567 | COMPLETE | 100% | MS Teams Update - Upcoming Training |  |  |  | Awareness
#REF!
#REF!
| #REF! | Wave 2 | Wave 1 End Users | 2020-11-09 | -553 | COMPLETE | 100% | MS Teams Update - Upcoming Training |  |  |  | Awareness
#REF!
#REF!
| #REF! | Partner/collaborators | Partners | 2020-11-16 | -546 | COMPLETE | 100% | Project update, training approach/plan, key dates |  |  |  | Awareness
| #REF! | Customers | Partners | 2020-12-14 | -518 | COMPLETE | 100% | Training email/instructions |  |  |  | Awareness
| #REF! | Customers | Partners | 2021-01-11 | -490 | COMPLETE | 100% | Partner check in |  |  |  | Reinforcement
#REF!
#REF!
Formulas:
DAYS LEFT = [DUE DATE]-TODAY()
DUE DATE = [DUE DATE, row below]-7
DUE DATE = [DUE DATE, row above]+7

## Assumptions
Key Dates |  |  | SUN | MON | TUE | WED | THU | FRI | SAT
Training
|  |  | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24
|  |  | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31
|  |  | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07
|  |  | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14
| End of Year Shutdown |  | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21
|  |  | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28
|  |  | 2020-11-29 | 2020-11-30 | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05
|  |  | 2020-12-06 | 2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12
|  |  | 2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19
|  |  | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26
Training Sessions |  |  | 2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | 2021-01-01 | 2021-01-02
|  |  | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09
|  |  | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16
|  |  | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23
|  |  | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30
|  |  | 2021-01-31 | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06
Questions |  |  | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13
| Where to post OCM working material? |  | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20
|  |  | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27
| Project plan & milestones? |  | 2021-02-28 | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06
| BRD? |  | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13
| SteerCo meeting dates? |  | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20
|  |  | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27
| What languages are we required to translate? What are the lead times? |  | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-03
|  | Mexico - Spanish | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10
|  | Argentina - Spanish | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17
Spain - Spanish
Brazil - Portuguese
Germany - German
China - Mandarin Chinese
French - French
Canada - French?
Can we "slice" distribution lists by:
Country/Wave
End Users vs. Supervisors/Managers
How do we identify collaboration partners (e.g., agencies) by wave?
When/how will we train partners?
Any mac users out there?