## Training Approach
| -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | + 1 | + 2
| 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25
Leadership Overviews | bar: 2020-03-16 to 2020-03-23
Team Reviews (Change Summary) | bar: 2020-03-30 to 2020-04-06
Process Overview, Rituals & Routines, Handoffs | bar: 2020-04-13 to 2020-04-20
Leading Through Change | bar: 2020-04-13 to 2020-04-20
End User Training | bar: 2020-04-06 to 2020-05-04
Advanced Topics | bar: 2020-05-18 to 2020-05-25
Project Updates
Change Plans (Executive Snapshot)
Change Summary (Team Level)
Process Overview, Rituals & Routines & Handoffs
Leading Through Change (for People Leaders)
Training - How to do my job?
Job Aids, Refresher & Adv Topics

## P2 Training Planning
| # | COURSE | COURSE NAME # | CONTENT | TOPICS COVERED | REQUIRED PARTICIPANTS | OPTIONAL PARTICIPANTS | CRITICAL ONSITE | WHERE | WEEK OF | TRAINER | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | Displ | T | W | R | F | UPDATES / NOTES | Schedule OK | Save the date | + Participants | + Zoom | Link to PPTX | Review PPTX | Knowledge ü | Reminder | Reminder DATE | Survey | Next Steps
[12 empty] | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01
x | 01 | Demand_Planning | 01_Demand_Planning | Demand Planning | [36 empty] | -7
x | 02 | DC_Allocation | 02_DC_Allocation | DC Allocation | [36 empty] | -7
x | 03 | Supply_Planning | 03_Supply_Planning | Supply Planning | [36 empty] | -7
| 04 | GCB_MMCD_Supply_Planning | 04_GCB_MMCD_Supply_Planning | GCB MMCD Supply Planning
x | 05 | Material_Planning | 05_Material_Planning | Material Planning | [36 empty] | -7
x | 06 | Deployment | 06_Deployment | Deployment | [36 empty] | -7
x | 07 | 3PM_Deployment | 07_3PM_Deployment | 3PM Deployment, Turnkey, Subcon Vendor | [36 empty] | -7
x | 08 | Shuttledock_for_Deployment | 08_Shuttledock_for_Deployment | Shuttledock (for deployment) | [36 empty] | -7
x | 09 | BluJay_PTM | 09_BluJay_PTM | BluJay for PTM | [36 empty] | -7
x | 10 | POP_Capacity | 10_POP_Capacity | POP + Capacity | [36 empty] | -7
x | 11 | Production_Scheduling | 11_Production_Scheduling | In-House Production Scheduling + Shuttledock Production Upload | [36 empty] | -7
x | 12 | Shuttledock_General | 12_Shuttledock_General | Shuttledock - General Training (end to end) | [36 empty] | -7
x | 13 | Production_Packet | 13_Production_Packet | Quality - Production Packet Creation | [36 empty] | -7
x | 14 | Quality_Hold | 14_Quality_Hold | Quality HOLD | [36 empty] | -7
x | 15 | Shuttledock | 15_Shuttledock_Ship_Complete | Shuttledock Ship Complete | [36 empty] | -7
x | 16 | Inhouse_Inventory_Transactions | 16_Inhouse_Inventory_Transactions | In-House Inventory Transactions (COGI, cycle counts, Production Posting) | [36 empty] | -7
x | 17 | Inhouse_Receiving | 17_Inhouse_Receiving | In-house Receiving | [36 empty] | -7
x | 18 | Route_Creation | 18_Route_Creation | Route creation | [36 empty] | -7
x | 19 | CM_Prod_Process_B2B_Cycle_Counts | 19_CM_Prod_Process_B2B_Cycle_Counts | Book to Book + Cycle Counts | [36 empty] | -7
x | 20 | CM_Prod_Inventory_Transactions_ErrorHandling | 20_CM_Prod_Inventory_Transactions_ErrorHandling | CM Inventory + Receipt Transactions + Error Handling | [36 empty] | -7
x | 21 | Export | 21_Export_Orders | Export | [36 empty] | -7
x | 22 | Transportation | 27_Transportation | Transportation | [36 empty] | -7
x | 23 | ATP Planning | 22_ATP Planning | ATP Planning | [36 empty] | -7
A | 23 | New_Product_Customer_Geography_Hierarchy | 23_New_Product_Customer_Geography_Hierarchy | New Product / Customer / Geography Hierarchy | [36 empty] | -7
x | 24 | Displays_Sales_BOM | 24_Displays_Sales_BOM | Displays/Sales BOMs | [36 empty] | -7
x | 25 | Whse_3PL | 25_Whse_3PL | Warehousing (includes whse for 3PL | [36 empty] | -7
x | 26 | Whse_MW_ | 26_Whse_MW_ | Warehouse Midwest & - Warehousing | [36 empty] | -7
C | 28 | Costing | 28_Costing | Costing | [7 empty] | 2020-04-06: SF 8-12 | [9 empty] | -7
C | 29 | Actual_Costing_Tasks | 29_Actual_Costing_Tasks | PAD Actual Costing Tasks (not training) | [36 empty] | -7
C | 30 | Finance_101 | 30_Finance_101 | Finance SAP 101 | [36 empty] | -7
C | 31 | Supply_Chain_Finance | 31_Supply_Chain_Finance | Supply Chain Finance | [36 empty] | -7
C | 32 | Sales_Finance | 32_Sales_Finance | Sales Finance | [36 empty] | -7
C | 33 | FP&A | 33_FP&A | FP&A - BPC refresher | [36 empty] | -7
C | 34 | GL | 34_GL | GL | [36 empty] | -7
C | 35 | Mfg_Acctg | 35_Mfg_Acctg | Manufacturing Accounting | [36 empty] | -7
C | 36 | AR | 36_AR | AR | [36 empty] | -7 | bar: 2020-04-06
N | 37 | Vendor_Master_Setup | 37_Vendor_Master_Setup | Vendor Master Set Up (internal) | [36 empty] | - | ?
N | 38 | AP_Coordination | 38_AP_Coordination | AP Coordination with Vendors (see comms dates) | [36 empty] | ?
N | 39 | Procurement | 39_Procurement _Indirect | Procurement | [36 empty] | -7
| 40 | Procurement_Direct | 40_Procurement_Direct
N | 41 | Web_Forms_Vendor_Training | 41_Web_Forms_Vendor_Training | Web Forms Vendor Training | [36 empty] | -7
N | 42 | SharePoint_for_PIH_Forecasts | 42_SharePoint_for_PIH_Forecasts | How to use SharePoint to share PIH & Forecasts (internal & external) | [36 empty] | -7
N | 43 | Plan_&_Procure | 43_Plan_&_Procure | Planning & Procurement - cross functional session | [36 empty] | -7
A | 44 | Master_Data | 44_Master_Data | Master Data Core Team | [36 empty] | -7
A | 45 | Prod_Setup_Commercialization | 45_Prod_Setup_Commercialization | Product Setup & Commercialization (PLM, new item set up process)
R | 46 | Customer_Fulfillment | 46_Customer_Fulfillment | Customer Fulfillment | [28 empty] | ?
R | 47 | Customer_Supply_Chain | 47_Customer_Supply_Chain | CSC overview, process, day-in-life | [27 empty] | Miguel will check with Raychel | ?
R | 48 | Customer_Master_Setup | 48_Customer_Master_Setup | Cust Master | [27 empty] | Miguel will check with Raychel/Ann G | ?
Waiting for WS Lead
Validate date/participants
Date/Participants Validated
Participants Added
Complete
NOT NEEDED
Formulas:
Reminder DATE = [WEEK OF]-7