## Project plan
Make Smoking History Project Plan [insert organisation here]
This plan will help track the ongoing activities to achieve the objectives of the project. New deliverables and outputs can be added to the plan, as appropriate for the organisation.
Project leader:
Steering group members:
Project leader, steering group members and Cancer Council WA representative will catch up (i.e. the first Monday of every month):
Status legend
Red (R) - output is delayed or undelivered
Amber (A) - at risk of not being delivered
Green (G) - on track
Blue (B) - complete
Outcomes | Deliverables | Outputs | Month (mark 'X' to schedule) | [11 empty] | Additional notes | Person responsible | Status
What are the desired results of project? | What is the project developing? (include other outputs) | What actions are undertaken to produce deliverables? (include other outputs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | What tasks are required to achieve outputs? | Who is leading this action?
Implement and promote a comprehensive tobacco policy | Smoking policy | Implement and/or edit the smoking policy | [12 empty] | Policy template is available from Make Smoking History
Disseminate and promote policy to all staff, clients, volunteers and contractors
Promote a smoke-free culture | Group tobacco information sessions | Implement weekly group tobacco information sessions for clients interested in reducing and quitting smoking
| Quitting case studies | Celebrate reduce and quit stories within organisation (e.g., staff intranet, celebration board, resident meetings)
| Updated statement in JDF | Include a statement that demonstrates organisation's smoke-free environment in staff job advertisements
Expand smoke-free environments | Smoke-free areas | Reduce smoking areas and make smoke-free areas more attractive and social
| Smoke-free signage | Display smoke-free signage in all smoke-free areas | [12 empty] | Make Smoking History can provide up to $200 to services for signage
| Quit smoking resources | Display quit smoking resources in common areas | [12 empty] | Quit smoking resources are available from Make Smoking History
Build capacity and confidence of staff to address smoking | Staff training | All staff to complete relevant brief advice online and face-to-face training | [12 empty] | Staff brief advice training is available for free from Make Smoking History
| Group tobacco information facilitator training | Relevant staff trained to deliver tobacco information sessions in group settings | [12 empty] | Group tobacco information sessions facilitator training available from Make Smoking History
Embed quit smoking support into processes and procedures | Updated client induction process | Incorporate information about smoke-free areas and available quit support into client induction process
| Updated case management notes | Include prompts to talk about tobacco use in client case management or recovery notes | [12 empty] | Examples of questions and prompts are available from Make Smoking History
| Referral pathways to NRT & Quitline | Design referral pathways for clients to access NRT and Quitline | [12 empty] | Make Smoking History can provide a budget to services for NRT products
| Updated staff induction process | Incorporate information about tobacco policy, available quit support, and training into staff induction process
Monitor and evaluate quit smoking support | Updated entry and exit documents | Include smoking related question at entry and exit documents or client database
Project aim 1:
To provide everyone at the service with access to quit information and support by the end of the project.
Project aim 2:
To increase smoke-free areas at the service by the end of the project.

## Organisation engagement plan
Organisational engagement plan for [insert name of organisation]
This plan will help track the ongoing engagement of the whole organisation throughout the project cycle.
Status legend
Red (R) - output is delayed or undelivered
Amber (A) - at risk of not being delivered
Green (G) - on track
Blue (B) - complete
Organisation engagement areas | Engagement steps | Month (mark 'X' to schedule) | [11 empty] | Additional notes | Person responsible | Status | Date
| What actions are undertaken? | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | What tasks are required to achieve this step? | Who is leading this steps? |  | What date was action undertaken?
Early engagement | Appoint project leader at the organisation
Initial meetings with executive and other senior management
Sign off MoU agreement by both Make Smoking History and organisation
Appoint project steering group
Promote organisation logo on Make Smoking History website
Project briefing and question time at team meetings
Pre-project evaluation | Pre-project organisational survey sent to service managers via project leader
Pre-project staff survey link sent to all staff via senior management
Staff and organisational pre-project surveys close
Staff and organisational pre-project surveys analysed and reports developed
Meeting with steering group to discuss survey results and project plan
Planning engagement | Consult with relevant staff, volunteers, clients, and external partners on project plan
Marketing and communications | Promote project successes on intranet, website, social media, e-news, annual report
Publish project testimonial on Make Smoking History website
Joint media release on project sent out
Quality improvement (progress evaluation) | Progress organisational survey sent to service managers via project leader
Progress staff survey link sent to all staff via senior management
Staff and organisational progress surveys close
Staff and organisational progress surveys analysed and reports developed
Meeting with steering group to discuss survey results and review project
Post-project evaluation | Post-project organisational survey sent to service managers via project leader
Post-project staff survey link sent to all staff via senior management
Staff and organisational post-project surveys close
Staff and organisational post-project surveys analysed and reports developed
What is organisational engagement:
The basis to successfully create change is ensuring that the people affected by the project are involved in the project. Throughout the project, it is imperative to involve all stakeholders.

## Stakeholder analysis matrix
Stakeholder analysis matrix for [insert name of organisation]
This matrix will help identify and analyse stakeholders for the project.
Stakeholder title | Contact person | Impact | Influence | What is important to the stakeholder? | How could the stakeholder contribute to the project? | How could the stakeholder block the project? | Strategy for engaging the stakeholder
Role | Name, Phone, Email | How much does the project impact them? (Low, Medium, High) | How much influence do they have over the project? (Low, Medium, High)

## Communications plan
Communications plan for [insert name of organisation]
This plan will help track the ongoing communication with relevant stakeholders throughout the project cycle.
Date | Stakeholder's name | Type of communication | Matter discussed | Outcome | Actions