## Sheet1
GASB 87 IMPLEMENTATION ROADMAP (STEP 1)
| GASB 87 Implementation Steps | Total Weeks Needed | Weeks Remaining | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
STEP 2 | Collecting and Organizing Leases Responsible Parties: Mary, Accounting and Jeff, Legal | 2 | 2 | bar: Week 1 to Week 2
STEP 3 | Extracting the Data Responsible Parties: Mary, Accounting and Department Leaders | 2 | 2 | bar: Week 2 to Week 3
STEP 4 | Crafting the Initial Schedules Responsible Parties: Mary, Accounting and Michele, Accounting | 2 | 2 | bar: Week 4 to Week 5
STEP 5 | Launching the Internal Review Process Responsible Parties: Jeff, Finance and Stacy, Accounting | 3 | 3 | bar: Week 6 to Week 8
STEP 6 | Understanding the Importance of Journal Entries Responsible Parties: Mary, Accounting | 1 | 1 | bar: Week 9
STEP 7 | Starting the External Review Process Responsible Parties: External CPAs | 2 | 2 | bar: Week 10 to Week 11
STEP 8 | Preparing Note Disclosures Responsible Parties: Susan, Financial Reporting | 2 | 2 | bar: Week 11 to Week 12
STEP 9 | Adhering to Ongoing Compliance Responsible Parties: Mary, Accounting and Department Leaders | 9 | 9 | bar: Week 1 to Week 12