## Projects
Gray cells will be calculated for you. You do not need to enter anything in them.
[12 empty] | -84768 | 2184
Proj ID | Owner | Project Name | Project Task | Category | Priority | Status | Start Date | Expected End Date | Actual End Date | Duration (days) | Completion % | Estimated Work (hrs) | Actual Work (hrs) | Budget Amount | Actual Amount
1 | Usr1 | Server upgrades |  | Software | 1-High | Started | 2020-11-07 10:30 | 2020-12-22 |  | 45 | 60% | 360 | 340 | 65000
1 | Usr1 | Server upgrades | New servers | Hardware | 1-High | Started | 2020-11-07 10:30 | 2020-12-02 | 2020-11-10 | 25 | 100% | 200 | 210 | 42000 | 44000
1 | Usr1 | Server upgrades | New servers | Software | 1-High | Risk | 2020-11-10 | 2020-12-18 |  | 38 | 70% | 304 |  | 12000
1 | Usr1 | Server upgrades | Re-do cables | Hardware | 1-High | Started | 2020-11-07 10:30 | 2020-12-04 | 2020-11-22 | 27 | 100% | 216 | 188 | 8000 | 6300
1 | Usr1 | Server upgrades | Cable runs | Labor | 1-High | Started | 2020-11-07 10:30 | 2020-12-12 |  | 35 | 80% | 280 | 310 | 7000
2 | Usr1 | Software port |  | Software | 1-High | OK | 2020-10-06 | 2017-01-11 |  | -1345 | 100% | -10760 |  | 12000
2 | Usr1 | Software port | initial spec | Software | 1-High | OK | 2020-10-06 | 2020-11-10 | 2020-11-07 | 34 | 100% | 272 | 260 | 2000
2 | Usr1 | Software port | design validate | Software | 1-High | OK | 2020-10-25 | 2020-11-15 | 2020-11-15 | 20 | 100% | 160 | 160 | 3000
2 | Usr1 | Software port | coding | Software | 1-High | Started | 2020-11-02 | 2020-12-03 | 2020-11-22 | 31 | 100% | 248 | 220 | 9000 | 7400
2 | Usr1 | Software port | Uat | Software | 1-High | Started | 2020-12-05 | 2017-01-06 |  | -1409 | 20% | -11272 |  | 9000
2 | Usr1 | Software port | install | Software | 1-High | Started | 2020-01-06 | 2020-01-11 |  | 5 | 0% | 40 |  | 9000
3 | Usr1 | VPN Install |  | Hardware | 2-Medium | OK | 2020-12-01 | 2017-01-22 |  | -1389 | 100% | -11112 |  | 12000
3 | Usr1 | VPN Install | RFQ | Hardware | 2-Medium | OK | 2020-12-01 | 2020-12-22 |  | 21 | 100% | 168 |  | 2000
3 | Usr1 | VPN Install | Vendor Select | Hardware | 2-Medium | Started | 2020-12-15 | 2020-12-24 |  | 9 | 100% | 72 |  | 3000
3 | Usr1 | VPN Install | Configuration | Hardware | 2-Medium | Started | 2020-01-02 | 2020-01-12 |  | 10 | 100% | 80 |  | 9000
3 | Usr1 | VPN Install | Deploy | Hardware | 2-Medium | Started | 2020-01-12 | 2020-01-22 |  | 10 | 20% | 80 |  | 9000
4 | Usr2 | Optical disk |  | Hardware | 1-High | OK | 2020-11-15 | 2020-12-10 |  | 25 | 60% | 200 |  | 33000
4 | Usr2 | Optical disk | RFQ | Hardware | 1-High | OK | 2020-11-15 | 2020-11-20 | 2020-11-10 | 5 | 100% | 40 | 40 | 0 | 44000
4 | Usr2 | Optical disk | POC | Software | 1-High | Started | 2020-11-22 | 2020-11-28 | 2020-12-02 | 6 | 70% | 48 | 48 | 3000 | 2500
4 | Usr2 | Optical disk | Vendor Select | Hardware | 1-High | Started | 2020-12-02 | 2020-12-04 |  | 2 | 100% | 16 | 188 | 28000 | 6300
4 | Usr2 | Optical disk | install | Labor | 1-High | Started | 2020-12-06 | 2020-12-10 |  | 4 | 80% | 32 |  | 2000
5 | Usr2 | Software Upgrade |  | Software | 2-Medium | OK | 2020-10-06 | 2017-01-11 |  | -1345 | 40% | -10760 |  | 76000
5 | Usr2 | Software Upgrade | Install | Software | 2-Medium | Started | 2020-11-02 | 2020-12-03 | 2020-11-22 | 31 | 100% | 248 | 220 | 35000 | 31000
5 | Usr2 | Software Upgrade | Uat | Software | 2-Medium | Started | 2020-12-05 | 2017-01-06 |  | -1409 | 20% | -11272 |  | 9000
5 | Usr2 | Software Upgrade | install | Software | 2-Medium | Started | 2020-01-06 | 2020-01-11 |  | 5 | 0% | 40 |  | 9000
6 | Usr2 | OS Deploy |  | Software | 1-High | OK | 2020-11-14 | 2017-02-22 |  | -1342 | 30% | -10736 |  | 12000
6 | Usr2 | OS Deploy | Spec | Software | 1-High | OK | 2020-12-01 | 2017-01-11 |  | -1400 | 20% | -11200 |  | 2000
6 | Usr2 | OS Deploy | Validate | Software | 1-High | Risk | 2020-12-15 | 2017-02-01 |  | -1394 | 10% | -11152 |  | 3000
6 | Usr2 | OS Deploy | Configuration | Software | 1-High | Started | 2014-01-02 | 2014-02-10 |  | 38 | 0% | 304 |  | 9000
6 | Usr2 | OS Deploy | Deploy | Software | 1-High | Started | 2014-02-11 | 2014-02-22 |  | 11 | 0% | 88 |  | 9000
Current Projects Plan

## README
This workbook is an application template which you can use with Excel Cloud.
Here's how to use Excel Cloud:
1. Download and install the Excel Cloud Product for Excel Windows. Click on the Download Page button below and download either the Windows or Mac installer.
2. Click Excel Cloud on the Excel ribbon menu.
3. Click on Login/Register command in the ribbon menu. If this is the first time you have used Excel Cloud, then click on the New User -> Register link to establish your user credentials.
4. Click on Excel worksheet tab you want to share. In this case, the Projects tab. Click on the Share Worksheet command to save the worksheet data to the secure Excel Digital Ledger cloud.
5. Click on Share My Workbook. This will create an email with the workbook as an attachment. Put in the email addresses of the people you want collaborate with, then send them the email. You only need to do this once.
6. You can now share your changes with collaborators by clicking on Submit. To see changes from others, click on Refresh.
You are all set – you can now share Excel information easy, simple, fast.
Any questions? email support@boardwalktech.com
You can delete this README tab at any time.
Click to Visit Installer Download Page
Click to Watch a YouTube Getting Started Video
Click to Visit Help Page & Download Getting Started Guide