FY2021 (7/1/20 – 6/30/21) Annual Work Plan

#### Pacific Conservation District

For More Information Contact: Mike Nordin, 360-208-4451, plutroll@willapabay.org

Mission of the Pacific Conservation District

- The Pacific Conservation District promotes sound; volunteer conservation programs and provides technical assistance to foster a healthy relationship between people and the environment through non-regulatory, voluntary, and incentive-based programs.

Natural Resource Priorities

- Watershed health

- Reduction in TMDL listings within the WRIA’s # 24 and 25

- Increase Salmonid habitat throughout Pacific Conservation District

- Cropland/unimproved land, tidelands and forest health

- Improve forest health for Pacific  Conservation District’s non-industrial private forest landowners (NIPF)

- Minimize pesticide contaminant of surface water from applications

- Assist in upgrading shellfish grounds

- Improve cropland/unimproved land/small AG operations farms

- Energy efficiency and conservation; Stormwater

- Reduce usage of non-renewable energy

- Educate about Low Impact Development and implement Low Impact Development

Information – Education & District Operations Priorities, Measures of Success, and Goals:

Education (continued goals):

- Goal 1 – Have an established education program for K-12 through adult.  Envirothon

- Goal 2 – A video that shows the relationship between conservation and natural resources

- Goal 3 – Create an education program that connects with state STEM requirements

- Goal 4 – Connect schools with Envirothon opportunities and natural resource career paths

- Goal 5 – Put together a scholarship fund for local kids to raise the profile of conservation and natural resources

- Goal 6 – Education and outreach program for the district

#### FY2011 (FY2020 (7/1/20 – 6/30/21) Annual Work Plan

Pacific Conservation District

Natural Resource Priority Program Area:  Watershed Health

Goal(s): Reduction in TMDL listings within the WRIA’s # 24 and 25

Increase Salmonid habitat throughout Pacific Conservation District

Natural Resource Measurable Result Objective:  No new TMDL listings & Improve riparian habitat

Programmatic Measurable Result Objective:  provide TA to a minimum of 10 cranberry, 10 non-dairy livestock producers, & 19 Salmonid Projects

Funding Source(s): Conservation Commission Grant Programs, CREP funds, RCO, WDFW, Pacific County

| Activities for FY2020 | ### Target Dates | Person Responsible | Time(Days) Required | Estimated Funding | Notes |
| --- | --- | --- | --- | --- | --- |
| riparian forest buffer Plantings by 10 acres | End of FY 20’ | D. Houk/J. Getchman | 200 | See Budget |  |
| T/A for 5 NMP’s and/or ISP’s or farm plans | End of FY 20’ | C. Hagain/ M. Martin-Aust | 418 | See Budget |  |
| Expand water quality testing program | End of FY 20’ | M. Nordin | 40 | See Budget |  |
| correct 2 salmonid barriers | End of FY 20’ | D. Marcell/T. Kollasch | 775 | See Budget |  |
| 2-5 CREP contracted to go on the ground or renewed | End of FY 20’ | C. Hagain | 600 | See Budget |  |
| 3 LWD project designed & permitted | End of FY 20’ | D. Marcell/T. Kollasch | 960 | See Budget |  |
| Complete Phase 2 of the North Cove Dynamic Revetment Project | End of FY 20’ | M. Nordin | 400 | See Budget |  |
| Continue to coordinate the PC VSP Program | On Going | M Martin-Aust | 1420 |  |  |
| Continue to coordinate the Pacific County Marine Resources Comm. | On Going | C. Hagain | 436 | See Budget |  |
| Continue to coordinate the Willapa Lead Entity Program | On Going | T. Kollasch | 700 | See Budget |  |
| Complete 2 Salmonid Assessment projects | End of FY 20’ | T. Kollasch/D. Marcell | 240 | See Budget |  |
| Complete/implement 12 Fish Screen replacements for irrigation sites | End of FY 19’ | D. Marcell/M. Martin-Aust | 70 | See Budget |  |

Natural Resource Priority Program Area:  Cropland/unimproved land, tidelands and forest health

Natural Resource Goal(s):

Improve forest health for Pacific Conservation District’s non-industrial private forest landowners (NIPF)

Minimize pesticide contaminant of surface water from applications

Assist in upgrading shellfish grounds

Improve cropland/unimproved land/small AG operations farms

Natural Resource Measurable Result Objective:  Improved Water quality for agricultural & Forestry production

Programmatic Measurable Result Objective:  provide technical assistance for 10 non-industrial private forest landowners (NIPF) & 2 agricultural operations

Funding Source(s): WSCC, RCPP, FFFPP, VSP, WSDA, Pacific County

| Activities for FY2020 | ### Target Dates | Person Responsible | Time(Days) Required | Estimated Funding | Notes |
| --- | --- | --- | --- | --- | --- |
| technical assistance and/or financial assistance to 10 non-industrial private forest landowners (NIPF) | End of FY 20’ | D. Houk/ J. Getchman | 200 | See Budget |  |
| correct 1 salmonid barriers using funding from FFFPP | End of FY 20’ | B. Carman | 120 | See Budget |  |
| Establish a district Fuels Reduction Program in Pacific County | End of FY 20’ | M. Nordin | 40 | See Budget |  |
| covered ditches in cranberry bogs properly and actively maintained | On Going | C. Hagain | 80 | See Budget |  |
| T/A to cranberry producers to install 5 BMP | End of FY 20’ | C. Hagain | 80 | See Budget |  |
| Work with Shellfish Producers NPDS and Invasives Control Program | On Going | M. Nordin | 40 | See Budget |  |
| technical assistance to 2 small agricultural operations | End of FY 20’ | C. Hagain/M. Martin-Aust | 240 | See Budget |  |
| acquire a no-till drill and make it available for landowners | End of FY 20’ | All Staff | 40 | See Budget |  |
| Continue to work on goal and deliverables for the VSP program | On Going | M. Martin-Aust | 1420 | See Budget |  |

Natural Resource Priority Program Area:  Energy efficiency and conservation; Stormwater

Goal(s):

Reduce usage of non-renewable energy

Educate about Low Impact Development and implement Low Impact Development

Natural Resource Measurable Result Objective:

Programmatic Measurable Result Objective:

Funding Source(s): Conservation Commission, ECY, NRCS

| Activities for FY2020 | ### Target Dates | Person Responsible | Time(Days) Required | Estimated Funding | Notes |
| --- | --- | --- | --- | --- | --- |
| Partner with NRCS to provide energy audits to 2 AG producers | End of FY 20’ | C. Hagain | 180 | See Budget |  |
| begin to provided information about Low Impact Development to a wide network of stakeholders | End of FY 20’ | All Staff | 120 | See Budget |  |

FY2020 Annual Budget

#### Pacific Conservation District

PCD Continued next page