## Roadmap
CASIC Workplan 2021
Objective | Activity | Milestone as per RoadMap | CASIC Deliverables 2021 | 2021 | [18 empty] | 2022 - 2024
|  |  |  | Aug |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
|  |  |  | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Strategic Objective 1: To strengthen CASIC and coordinate relevant stakeholders
1.1. CASIC strengthened and its sub-committees supported | 1.1.1. Conduct CASIC meetings | Semester and annual Steering Committee (SC) meetings | 1 SC meting held
|  | Monthly Executive Board (EB) meetings | 3 Eb meetings held
|  | Quarterly sub-committee meetings | Will start from 2022
| 1.1.2. Organize CASIC field visits | Two field visits per year of SC with participation from EB and sub-committee members | 1 field visits conducted
|  | Two field visits per year of EB with participation from relevant stakeholders | 1 field visit conducted
1.2. Policy dialogues strengthened for CA & SI and agroecology integration and uptake | 1.2.1. Conduct an economic impact assessment of CA & SI and agroecological adoption to policy makers | Report on economic impact assessment and policy briefs (completed and disseminated) | 1 case study report
| 1.2.2. Conduct national public-private sector forums | Annual public-private sector forum | Will start from 2022
| 1.2.3. Work with NAP-Secretariat for complementary effort and joint activities to combat agricultural land degradation | CA & SI and agroecology in response to NAP implementation | Will start from 2022
| 1.2.4. Work with MAFF to include CA & SI and agroecology in the agriculture related policies, strategies and plans | At least 15 percent of strategic documents included CA & SI and agroecology terms | Will start from 2022
| 1.2.5. Enhance cooperation with DEAFF, GDA and MAFF to engage PDAFFs to conduct CA and SI extensions | At least 8 provinces where extensions conducted by PDAFFs (strengthening the existing engagement in Battambang, Preah Vihear, Kampong Thom, and Kampong Cham, and scaling up to other 4 potential provinces including Siem Reap, Kampong Speu, Tboung Khmum, and Kratie) | 8 provinces coorperate with
| 1.2.6. Establish cooperation with MoE and NCSD by linking CA & SI and agroecology with NBSAP and NDC | Research-based policy briefs (produced and disseminated) | Will start from 2022
|  | CA & SI and agroecology applied at larger diversities of agroecosystems (100 hectares) | Will start from 2022
| 1.2.7. Liaise with existing policy dialogue platforms like Technical Working Group on Agriculture and Water, Technical Working on Climate Change in Agriculture, and National Dialogue on Sustainable Food System | Participation in the dialogue platforms = at least one time per platform per year | Will start from 2022
1.3. Regional collaboration maintained and strengthened | 1.3.1. Maintain current regional cooperation | Partnerships built with regional programs/platforms through conferences, workshops, trainings, study tours, joint research, etc. | Will start from 2022
| 1.3.2. Include expert groups to support capacity development of CASIC members and partners |  | Will start from 2022
| 1.3.3. Organize regional workshops / trainings / conferences | Regional workshops / trainings / conferences organized in collaboration with regional networks and/or partners | 1 regional workshop conducted
1.4. Financial sustainability reached | 1.4.1. Develop a sponsorship strategy for event-based fundraising | Sponsorship strategy (completed) | Completed
| 1.4.2. Explore existing and new financial mechanisms with other government agencies, private sector and development partners | Potential financial mechanisms explored and utilized | Will start from 2022
| 1.4.3. Maintain voluntary institutional contribution from the Steering Committee and Executive Board | Annual contribution for CASIC operation | Will start from 2022
| 1.4.4. Study membership structure and benefits, more particularly the feasibility in enforcement at a later stage of CASIC development | Study on membership structure and fees (completed and decided) | Completed
Strategic Objective 2: Knowledge and research on CA & SI and agroecology enhanced
2.1. Research results compiled with technology transfer approach for target audiences | 2.1.1. Develop CA & SI and agroecology database (or knowledge management system) | A CA & SI and agroecology database (or knowledge management system) up and running | A draft dashboard will be developed
| 2.1.2. Develop technical and educational materials (in collaboration with other sub-committees) | Technical and educational materials readily available for trainings and academic purposes | Will start from 2022
| 2.1.3. Share information via various platforms (closely linked with promotion function) | CA & SI and agroecology knowledge/information shared on various platforms and conferences | 2 times/week of facebook posting on CASIC page Weekly document uploaded on website or on demand basis
| 2.1.4. Support the integration of CA & SI and agroecology into national curriculum | At least 1 program of curriculum integrating CA & SI and agroecology | Will start from 2022
2.2. Research on different agroecosystems and new technologies to respond to climate resilience and economic motivation | 2.2.1. Support mechanisms to identify research priorities and to continue researches | At least 4 researches/ technologies to be developed and rolled out | Will start from 2022
| 2.2.2. Support research, conservation and sharing of staple and cover crop seeds | At least 46 species and 216 varieties of staple and cover crop seeds conserved | Will start from 2022
|  | At least 10 seed varieties shared with Technology Parks, universities and research centers | Will start from 2022
|  | Contribution to the official registration of the cover crops species into the national portfolio | Will start from 2022
| 2.2.3. Support the testing and adaptation of appropriate-scale mechanization and technologies | Appropriate-scale mechanization and technology tested and validated (associated with R4D) | Will start from 2022
| 2.2.4. Support the improvement of infrastructure and resources at Bos Khnor Station, other relevant research centers and universities | Bos Khnor promoted as a national research and training center on CA & SI and agroecology | Will start from 2022
|  | Research activities within other research stations and universities supported and promoted | Will start from 2022
2.3. Zoning of strategic areas prioritized for CA & SI and agroecology practices | 2.3.1. Conduct an agricultural land zoning assessment | An agricultural land zoning assessment report (completed and disseminated) | Will start from 2022
Strategic Object 3: CA & SI and agroecology services improved and scaled up
3.1. An innovative extension model promoted | 3.1.1. Promote an innovative extension model | Innovative extension model introduced and piloted | Will start from 2022
| 3.1.2. Conduct regular TOT trainings under the extension model | At least one TOT training per year | Will start from 2022
| 3.1.3. Work with government and donor-funded agriculture projects and programs | At least one orientation/training program on CA & SI and agroecology per year is introduced with agricultural projects and programs. | Will start from 2022
3.2. Awareness of stakeholders on CA & SI and agroecology enhanced | 3.2.1. Produce promotional videos/materials and post them on media, websites, and social media | • Two videos per year • Four leaflets per year • Four newsletters per year • 200 relevant documents (including articles, etc.) uploaded in CASIC’s website | Will start from 2022
| 3.2.2. Conduct round table discussions on TVs, radios, and social media platforms | Two TV/radio round table discussions per year | Will start from 2022
| 3.2.3. Conduct regular agriculture fairs and field visits for relevant stakeholders | One agriculture fair and two field visits per year | Will start from 2022
| 3.2.4. Support the conducts of field demonstrations with agriculture cooperatives | One field demonstration per year | Will start from 2022
3.3. Investment from private sector actors in supporting / engaging in CA & SI and agroecology-based production systems | 3.3.1. Conduct meetings/round-table discussions with and field visits for private sector | Two meetings/round-table discussions with private sector per year | Will start from 2022
| 3.3.2. Support private sector to improve access of farmers to technologies, finance and market linkages |  | Will start from 2022
| 3.3.3. Support study on financial mechanisms to reward farmers and private sector for their CA and SI adoption and engagement | Financial rewarding mechanisms (finalized and introduced) | Will start from 2022

## Weekly activity
CASIC Workplan 2021 (breakdown into week)
Month/Week | Objective No./ Activity No. | Activity | Secretariat Support | OIC | Deliverable
2021-08-01
Week 2 | 1.1/1.2.1 | Report on economic impact assessment and policy briefs (completed and disseminated) | Follow up with consultant team to get final report | Riya | Final report
|  |  | Process payment to consultant | Riya | Payment approval letter
| 3.2/3.2.1 | Produce promotional videos/materials and post them on media, websites, and social media | Draft newsletter template | Riya | Draft template
|  |  | Follow up with Dr. Saruth and finalize the template | Riya | Approved template
Week 3 | 1.1/1.1.1 | Conduct CASIC meetings | Create telegram group for all subcommittees with members | Riya and Vathana | 4 telegroups created
|  |  | Discuss with subcommittees lead for quaterly meeting preparation | Riya and Vathana | Proposed date and agenda
|  |  | Prepare agenda and invitation | Riya and Vathana | Approved agenda and invitation
|  |  | Prepare meeting document | Riya and Vathana | Ppt
| 2.1/2.1.3 | Share information via various platforms (closely linked with promotion function) | Follow up the draft of fb content with chair and post on facebook | Vathana and Dary
|  |  | Translate fb content to Khmer | Vathana and Dary | Khmer content
Week 4 | 1.1/1.1.1 | Conduct CASIC meetings | Organize two subcommitee meeting | Riya and Vathana | Two subcomm. Quarterly meetings
|  |  | Develop meeting minutes | Riya and Vathana | Meeting minutes
| 2.1/2.1.3 | Share information via various platforms (closely linked with promotion function) | facebook posting | Vathana and Dary
|  |  | Final the purchasing for website | Vathana and Dary
| 1.1/1.1.1 | Conduct CASIC meetings | Discuss with chair on 4rd EB meeting and prepare the meeting and send out to member | Dary | Agenda and invitation
| N/A | Secretarit monthly meeting with Chairman | Develop report template | Riya | Montly report template
|  |  | Prepare and organize montly meeting with chair | Riya | Secretariat monthly meeting
2021-09-01
Week 1 | 1.1/1.1.1 | Conduct CASIC meetings | Organize other two subcommitee meetings | Riya and Vathana | Two subcomm. Quarterly meetings
|  |  | Develop meeting minutes | Riya and Vathana | Meeting minutes
| 2.1/2.1.3 | Share information via various platforms (closely linked with promotion function) | facebook posting | Vathana and Dary
|  |  | finalize website and official host websit | Vathana and Dary | Official website
| 1.1/1.1.1 | Conduct CASIC meetings | Develop ppt for 4th EB meeting | Riya | Presentation slide
|  |  | Organize 4th EB meeting | Dary | EB meeting
|  |  | Develop meeting minutes | Dary | Minutes
| 1.3/1.3.3 | Organize regional workshops / trainings / conferences | Discuss and prepare regional workshop | Manith
| 2.1/2.1.1 | Develop CA & SI and agroecology database (or knowledge management system) | Discuss with MRM officer on building CASIC monitoring system | Riya, Manith and Borey
Week 2 | 1.3/1.3.3 | Organize regional workshops / trainings / conferences | Discuss and prepare two regional workshops | Manith
| 2.1/2.1.3 | Share information via various platforms (closely linked with promotion function) | Training on how to manage and run website from agency | Riya, Vathana, Dary, Manith | Traning session
| 2.1/2.1.3 | Share information via various platforms (closely linked with promotion function) | Fb post and website post | Vathana and Dary
| 2.1/2.1.1 | Develop CA & SI and agroecology database (or knowledge management system) | Discuss and draft CASIC monitoring system | Riya, Manith and Borey
| 3.2/3.2.1 | Produce promotional videos/materials and post them on media, websites, and social media | Develop CASIC newsletter | Riya | Draft newsletter
Week 3 | 2.1/2.1.1 | Develop CA & SI and agroecology database (or knowledge management system) | Draft CASIC monitoring system | Borey | Draft monitoring system
| 3.2/3.2.1 | Produce promotional videos/materials and post them on media, websites, and social media | Finalize and share newsletters | Riya | Approved newsletter
| 3.1/3.1.3 | Regional workshops / trainings / conferences organized in collaboration with regional networks and/or partners | Prepare and finalize two regional workshops | Manith | Final plan
| 2.1/2.1.3 | Share information via various platforms (closely linked with promotion function) | Fb post and website post | Vathana and Dary
Week 4 | 3.1/3.1.3 | Regional workshops / trainings / conferences organized in collaboration with regional networks and/or partners | Prepare two regional workshops | Manith
|  |  | Organize first regional workshop | Manith | First regional workshop conducted
|  |  | Develop report | Manith | Report
| 2.1/2.1.1 | Develop CA & SI and agroecology database (or knowledge management system) | Present draft monitoring system to Chairman | Borey
| N/A | Monthly meeting | Prepare and organize montly meeting with chair | Riya | Secretariat monthly meeting
| 1.1/1.1.1 | Conduct CASIC meetings | Discuss and prepare 5th EB meeting | Dary | Agenda and invitation
2021-10-01
Week 1 | 3.1/3.1.3 | Regional workshops / trainings / conferences organized in collaboration with regional networks and/or partners | Organize second regional workshop | Manith | Second workshop conducted
|  |  | Develop workshop report | Manith | Report
| 2.1/2.1.1 | Develop CA & SI and agroecology database (or knowledge management system) | Finalize monitoring system | Borey | Approved system
| 2.1/2.1.3 | Share information via various platforms (closely linked with promotion function) | Fb post and website post | Vathana and Dary
Week 2 | 1.1/1.1.1 | Conduct CASIC meetings | Develop ppt for 5th EB meeting | Riya | Presentaion slide
|  |  | Organize 5th EB meeting | Dary | 5th EB meeting
|  |  | Develop meeting minutes | Dary | Minutes
| 1.1/1.1.1 | Share information via various platforms (closely linked with promotion function) | Fb post and website post | Vathana and Dary
| 3.2/3.2.1 | Produce promotional videos/materials and post them on media, websites, and social media | Develop CASIC second-version leaflet | Riya | Approved leaftlet
|  |  | Draft subcommittees leaflet with subcommittees leads | Vathana and Dary | 4 draft leaflets
|  |  | Follow up with Comm on 3 CASIC new videos | Manith
Week 3 | N/A | Financial report | Develop and finalize financial report to CE SAIN | Riya | Final report
| 2.1/2.1.3 | Share information via various platforms (closely linked with promotion function) | Fb post and website post | Vathana and Dary
Week 4 | 3.2/3.2.1 | Produce promotional videos/materials and post them on media, websites, and social media | Finalize CASIC second-version leaflet | Riya | Approved leaftlet
|  |  | Finalize subcommitee leaflet | Vathana and Dary | Approved leaftlet
|  |  | Continue to work on 3 new videos with comm | Manith
| N/A | Monthly meeting | Prepare and organize monthly meeting with chair | Riya | Monthly meeting with chair
| 1.1/1.1.1 | Conduct CASIC meetings | Discuss with chair on 6th EB meeting | Dary | Agenda and invitation
2021-11-01
Week 1 | 3.2/3.2.1 | Produce promotional videos/materials and post them on media, websites, and social media | Finish the draft of all 3 new videos | Manith | draft videos
| 1.1/1.1.1 | Conduct CASIC meetings | Prepare ppt for 6th EB meeting | Riya | Presentation slide
|  |  | Organize 6th EB meeting | Dary | 6th EB meeting conducted
|  |  | Develop minutes | Dary | Minutes
| 1.1/1.1.1 | Share information via various platforms (closely linked with promotion function) | Fb post and website post | Vathana and Dary
Week 2 | 1.1/1.1.1 | Conduct CASIC meetings | Prepare subcommitee annual meeting | Riya and Vathana
|  |  | Draf subcommitees annual report | Vathana | Draft subcommitees annual report
|  |  | Follow with members for the update | Riya and Vathana | Updated monitoring system
|  |  | Work with leads on agenda and others | Riya and Vathana | Agenda and invitation
| 1.1/1.1.1 | Share information via various platforms (closely linked with promotion function) | Fb post and website post | Vathana and Dary
Week 3 | 1.1/1.1.1 | Conduct CASIC meetings | Prepare subcommitee annual meeting | Riya and Vathana
|  |  | Finalize subcommitees annual report | Vathana | Subcommitee annual report
|  |  | Follow with members for the update | Riya and Vathana | Updated monitoring system
|  |  | Work with leads on agenda and others | Riya and Vathana | Agenda and invitation
| 1.1/1.1.1 | Share information via various platforms (closely linked with promotion function) | Fb post and website post | Vathana and Dary
Week 4 | 1.1/1.1.1 | Conduct CASIC meetings | Draft CASIC annual report | Riya | Draft CASIC annual report
| 3.2/3.2.1 | Produce promotional videos/materials and post them on media, websites, and social media | Draft CASIC newsletter | Riya | Draft CASIC newsletter
| 1.1/1.1.1 | Share information via various platforms (closely linked with promotion function) | Fb post and website post | Vathana an Dary
| 1.1/1.1.1 | Conduct CASIC meetings | Organize two subcommitee annual meeting | Riya and Vathana | Two annual subcommittees conducted
|  |  | Develop report | Dary | report
| N/A | Monthly meeting | Prpare and organize monthly meeting with chair | Riya | Monthly meeting with chair
2021-12-01
Week 1 | 1.1/1.1.1 | Conduct CASIC meetings | Organize other two subcommittees annaul meeting | Riya and Vathana
|  |  | Develop annual report | Dary | Annual report
|  |  | Finalize CASIC annual report | Riya | Approved annual report
|  |  | Prepare CASIC annual meeting and field visit | Riya and Vathana and Dary | Approved agenda and invitation
| 3.2/3.2.1 | Produce promotional videos/materials and post them on media, websites, and social media | Finalize CASIC newsletter | Riya | Approved newsletter
Week 2 | 1.1/1.1.1 | Conduct CASIC meetings | Translate annual report to Khmer | Manith | Khmer report
|  |  | Prepare CASIC annual meeting materials and doc | Riya and Vathana and Dary
Week 3 | 1.1/1.1.1 | Conduct CASIC meetings | Organize annual meeting and field visit | Riya and Vathana and Dary | CASIC annual meeting conducted
|  |  | Develop annual report | Dary | CASIC annual report
Week 4 | N/A | Financial report | Draft financial report for Swisscontact | Riya | Draft financial report
| N/A | CASIC workplan 2022 | Draft CASIC workplan 2021 | Riya | Draft CASIC workplan 2022